## Sheet1
DIRECT CLIENT ASSISTANCE (DCA) - unreconciled
| Agency | DCA (February) | DCA (March) | DCA (April) | DCA (May) | DCA (June) | DCA (July) | DCA (August) | DCA (September) | DCA (October) | DCA (November) | DCA (December) | DCA (January) | DCA (February) | DCA (March) | DCA (April) | DCA (May) | DCA (June) | DCA (July) | DCA (August) | DCA (September) | Average monthly DCA | DCA YTD | ESG-CV DCA Budget | DCA adjustments* | FY21 Adjusted DCA Goal | % of Goal Met
| ABC | 0 | 0 | 0 | 0 | 0 | [15 empty] | 9320.9412 | 0 | 158456 |  | 158456 | 0% | June is 5 months into the contract. 20 months is 5% per month average. 5 months = 25%
| Caritas | 0 | 0 | 0 | 0 | 0 | [15 empty] | 33895.4276 | 0 | 576222.27 |  | 576222.27 | 0%
| FFH | 0 | 0 | 0 | 0 | 475.22 | [15 empty] | 22849.34 | 475.22 | 388914 |  | 388914 | 0.1222%
| FS | 0 | 0 | 0 | 0 | 0 | [15 empty] | 41462.4706 | 0 | 704862 |  | 704862 | 0%
| LW | 0 | 0 | 0 | 1573 | 1859.93 | [15 empty] | 43799.6512 | 3432.93 | 748027 |  | 748027 | 0.4589%
| SA | 0 | 0 | 0 | 0 | 0 | [15 empty] | 50836.2353 | 0 | 864216 |  | 864216 | 0%
| TSA | 0 | 0 | 0 | 0 | 0 | [15 empty] | 41462.4706 | 0 | 704862 |  | 704862 | 0%
| Vivent | 0 | 0 | 0 | 0 | 0 | [15 empty] | 15133.7647 | 0 | 257274 |  | 257274 | 0%
| TOTALS | 0 | 0 | 0 | 1573 | 2335.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258760.3012 | 3908.15 | 4402833.27 | 0 | 4402833.27 | 0.08876%
PERFORMANCE MEASURES (Output 1) -unreconciled
Clients Served
Agency |  | New Clients Served (Feb 2021) | New Clients Served (March 2021) | New Clients Served (April 2021) | New Clients Served (May 2021) | New Clients Served (June 2021) | New Clients Served (July 2021) | New Clients Served (Aug 2021) | New Clients Served (Sept 2021) | New Clients Served (Oct 2021) | New Clients Served (Nov 2021) | New Clients Served (Dec 2021) | New Clients Served (Jan 2022) | New Clients Served (Feb 2022) | New Clients Served (March 2022) | New Clients Served (April 2022) | New Clients Served (May 2022) | New Clients Served (June 2022) | New Clients Served (July 2022) | New Clients Served (Aug 2022) | New Clients Served (Sept 2022) | CLs Served YTD | Average per month to attain goal | Client Served Goal | Client Goal Adjustments | Adjusted Client Served Goal | % of Goal Met | June target % of Goal is 25%
ABC |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.4706 | 25 |  | 25 | 0%
Caritas |  | 0 | 0 | 0 | 4 | 0 | [15 empty] | 4 | 2.4118 | 45 |  | 45 | 8.889%
FFH |  | 0 | 0 | 0 | 15 | 4 | [15 empty] | 19 | 0.76471 | 32 |  | 32 | 59.38%
FS |  | 0 | 0 | 0 | 0 | 1 | [15 empty] | 1 | 2.5882 | 45 |  | 45 | 2.222%
LW |  | 0 | 0 | 0 | 4 | 0 | [15 empty] | 4 | 3.1765 | 58 |  | 58 | 6.897%
SA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 3.8235 | 65 |  | 65 | 0%
TSA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 3.2353 | 55 |  | 55 | 0%
Vivent |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.1765 | 20 |  | 20 | 0%
TOTALS |  | 0 | 0 | 0 | 23 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 18.6471 | 345 |  | 345 | 8.116%
Households Served
Agency |  | New HHs Served (Feb 2021) | New HHs Served (March 2021) | New HHs Served (April 2021) | New HHS Served (May 2021) | New HHs Served (June 2021) | New HHs Served (July 2021) | New HHs Served (Aug 2021) | New HHs Served (Sept 2021) | New HHs Served (Oct 2021) | New HHs Served (Nov 2021) | New HHs Served (Dec 2021) | New HHs Served (Jan 2022) | New HHs Served (Feb 2022) | New HHs Served (March 2022) | New HHs Served (April 2022) | New HHs Served (May 2022) | New HHs Served (June 2022) | New HHs Served (July 2022) | New HHs Served (Aug 2022) | New HHs Served (Sept 2022) | HHs Served YTD | Average per month to attain goal | HHs Served Goal | HH Goal Adjustments | Adjusted HHs Served Goal | % of Goal Met | June target % of Goal is 25%
ABC |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0.35294 | 6 |  | 6 | 0% | NOTE: Household served goal for the ESG is 250. Partner goals total 234, but total % of Goal is measured against the 250 program housed goal.
Caritas |  | 0 | 0 | 0 | 4 | 0 | [15 empty] | 4 | 1.9412 | 37 |  | 37 | 10.81%
FFH |  | 0 | 0 | 0 | 6 | 1 | [15 empty] | 7 | 0.64706 | 18 |  | 18 | 38.89%
FS |  | 0 | 0 | 0 | 0 | 1 | [15 empty] | 1 | 2.1176 | 37 |  | 37 | 2.703%
LW |  | 0 | 0 | 0 | 3 | 0 | [15 empty] | 3 | 2.1765 | 40 |  | 40 | 7.5%
SA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 2.7059 | 46 |  | 46 | 0%
TSA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 2.1765 | 37 |  | 37 | 0%
Vivent |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0.76471 | 13 |  | 13 | 0%
TOTALS |  | 0 | 0 | 0 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 13.8235 | 234 |  | 250 | 6%
Households Housed
Agency |  | HHs Housed (Feb 2021) | HHs Housed (March 2021) | HHs Housed (April 2021) | HHS Housed (May 2021) | HHs Housed (June 2021) | HHs Housed (July 2021) | HHs Housed (Aug 2021) | HHs Housed (Sept 2021) | HHs Housed (Oct 2021) | HHs Housed (Nov 2021) | HHs Housed (Dec 2021) | HHs Housed (Jan 2022) | HHs Housed (Feb 2022) | HHs Housed (March 2022) | HHs Housed (April 2022) | HHs Housed (May 2022) | HHs Housed (June 2022) | HHs Housed (July 2022) | HHs Housed (Aug 2022) | HHs Housed (Sept 2022) | HHs Housed YTD | Average per month to attain goal | Household Housed Goal | HH Housed Goal Adjustments | Adjusted HHs Housed Goal | % of Goal Met | June target % of Goal is 25%
ABC |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0.29412 | 5 |  | 5 | 0% | NOTE: Household housed goal for the ESG is 200. Partner goals total 190, but total % of Goal is measured against the 200 program housed goal.
Caritas |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.7647 | 30 |  | 30 | 0%
FFH |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0.88235 | 15 |  | 15 | 0%
FS |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.7647 | 30 |  | 30 | 0%
LW |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.8824 | 32 |  | 32 | 0%
SA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 2.1765 | 37 |  | 37 | 0%
TSA |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 1.7647 | 30 |  | 30 | 0%
Vivent |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | 0 | 0.64706 | 11 |  | 11 | 0%
TOTALS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.7647 | 190 |  | 200 | 0%
DAYS TO HOUSING
Days to housing - Starting from 2/1/21 - YTD | [21 empty] | Total housed | Average # of days* | Exited without move-in
ABC RRH | [21 empty] | 0 | 0 | 0 | Color key: Green denotes decrease in days. Red denotes increase in days. Black denotes no change.
Caritas RRH | [21 empty] | 0 | 0 | 0
FFH RRH | [21 empty] | 0 | 0 | 0
FS RRH | [21 empty] | 0 | 0 | 0
LW RRH | [21 empty] | 0 | 0 | 0
SA RRH | [21 empty] | 0 | 0 | 0
TSA RRH | [21 empty] | 0 | 0 | 0
Vivent RRH | [21 empty] | 0 | 0 | 0
Collaborative | [21 empty] | 0 | 0 | 0
*Collaborative average # of days to move-in from entry is total averages days/# of partners with RRH enrollments
Quarterly Data
Agency |  | Quarter 1 |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Quarter 5 |  |  | Quarter 6 |  |  | Quarter 7 |  |  | Goal = 80%
|  | HH served | HH housed | HH served | HH housed | Q2 % | HH served | HH housed | Q3 % | HH served | HH housed | Q4 % | HH served | HH housed | Q5 % | HH served | HH housed | Q6 % | HH served | HH housed | Q7 % | YTD total
ABC |  | 0 | 0
Caritas |  | 0 | 0
FFH |  | 0 | 0
FS |  | 0 | 0
LW |  | 0 | 0
SA |  | 0 | 0
TSA |  | 0 | 0
Vivent |  | 0 | 0
TOTALS |  | 0 | 0 | 0 | 0
Clients Served
Agency |  | Quarter 1 |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Quarter 5 |  |  | Quarter 6 |  |  | Quarter 7 |  |  | YTD total
ABC |  | 0 | [19 empty] | 0
Caritas |  | 0 | [19 empty] | 0
FFH |  | 0 | [19 empty] | 0
FS |  | 0 | [19 empty] | 0
LW |  | 0 | [19 empty] | 0
SA |  | 0 | [19 empty] | 0
TSA |  | 0 | [19 empty] | 0
Vivent |  | 0 | [19 empty] | 0
TOTALS |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0