## Sheet1
DIRECT CLIENT ASSISTANCE (DCA) - unreconciled
| Agency | DCA (February) | DCA (March) | DCA (April) | DCA (May) | DCA (June) | DCA (July) | DCA (August) | DCA (September) | DCA (October) | DCA (November) | DCA (December) | DCA (January) | DCA (February) | DCA (March) | DCA (April) | DCA (May) | DCA (June) | DCA (July) | DCA (August) | DCA (September) | Average monthly DCA | DCA YTD | ESG-CV DCA Budget | DCA adjustments* | FY21 Adjusted DCA Goal | % of Goal Met | Sept finance data as of 9/9/21 at 12:25 pm
| ABC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 9903.5 | 0 | 158456 |  | 158456 | 0% | September is 8 months into the contract. 20 months is 5% per month average. 8 months = 40%
| Caritas | 0 | 0 | 0 | 0 | 1322.83 | 0 | 4325.92 | 3029.3 | [12 empty] | 35471.5137 | 8678.05 | 576222.27 |  | 576222.27 | 1.506%
| FFH | 0 | 0 | 0 | 0 | 490.22 | 5431 | 8913.53 | 13822.2 | [12 empty] | 22516.0656 | 28656.95 | 388914 |  | 388914 | 7.368%
| FS | 0 | 0 | 0 | 0 | 0 | 5110.65 | 3429.84 | 0 | [12 empty] | 43520.0944 | 8540.49 | 704862 |  | 704862 | 1.212%
| LW | 0 | 0 | 0 | 0 | 1588.05 | 21.88 | 23402.46 | 6215.57 | [12 empty] | 44799.94 | 31227.96 | 748027 |  | 748027 | 4.175%
| SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 54013.5 | 0 | 864216 |  | 864216 | 0%
| TSA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 44053.875 | 0 | 704862 |  | 704862 | 0%
| Vivent | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | [12 empty] | 16077.4375 | 35 | 257274 |  | 257274 | 0.0136%
| TOTALS | 0 | 0 | 0 | 0 | 3401.1 | 10563.53 | 40106.75 | 23067.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270355.9262 | 77138.45 | 4402833.27 | 0 | 4402833.27 | 1.752%
PERFORMANCE MEASURES (Output 1) -unreconciled
Clients Served
Agency |  | New Clients Served (Feb 2021) | New Clients Served (March 2021) | New Clients Served (April 2021) | New Clients Served (May 2021) | New Clients Served (June 2021) | New Clients Served (July 2021) | New Clients Served (Aug 2021) | New Clients Served (Sept 2021) | New Clients Served (Oct 2021) | New Clients Served (Nov 2021) | New Clients Served (Dec 2021) | New Clients Served (Jan 2022) | New Clients Served (Feb 2022) | New Clients Served (March 2022) | New Clients Served (April 2022) | New Clients Served (May 2022) | New Clients Served (June 2022) | New Clients Served (July 2022) | New Clients Served (Aug 2022) | New Clients Served (Sept 2022) | CLs Served YTD | Average per month to attain goal | Client Served Goal | Client Goal Adjustments | Adjusted Client Served Goal | % of Goal Met | September target % of Goal is 40%
ABC |  | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | [12 empty] | 15 | 0.625 | 25 |  | 25 | 60%
Caritas |  | 0 | 0 | 0 | 4 | 1 | 2 | 1 | 2 | [12 empty] | 10 | 2.1875 | 45 |  | 45 | 22.22%
FFH |  | 0 | 0 | 0 | 15 | 7 | 2 | 11 | 0 | [12 empty] | 35 | -0.1875 | 32 |  | 32 | 109.4%
FS |  | 0 | 0 | 0 | 0 | 4 | 2 | 1 | 0 | [12 empty] | 7 | 2.375 | 45 |  | 45 | 15.56%
LW |  | 0 | 0 | 0 | 4 | 4 | 3 | 30 | 1 | [12 empty] | 42 | 1 | 58 |  | 58 | 72.41%
SA |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | [13 empty] | 8 | 3.5625 | 65 |  | 65 | 12.31%
TSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 6 | [12 empty] | 21 | 2.125 | 55 |  | 55 | 38.18%
Vivent |  | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | [12 empty] | 6 | 0.875 | 20 |  | 20 | 30%
TOTALS |  | 0 | 0 | 0 | 23 | 16 | 11 | 85 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 12.5625 | 345 |  | 345 | 41.74%
Households Served
Agency |  | New HHs Served (Feb 2021) | New HHs Served (March 2021) | New HHs Served (April 2021) | New HHS Served (May 2021) | New HHs Served (June 2021) | New HHs Served (July 2021) | New HHs Served (Aug 2021) | New HHs Served (Sept 2021) | New HHs Served (Oct 2021) | New HHs Served (Nov 2021) | New HHs Served (Dec 2021) | New HHs Served (Jan 2022) | New HHs Served (Feb 2022) | New HHs Served (March 2022) | New HHs Served (April 2022) | New HHs Served (May 2022) | New HHs Served (June 2022) | New HHs Served (July 2022) | New HHs Served (Aug 2022) | New HHs Served (Sept 2022) | HHs Served YTD | Average per month to attain goal | HHs Served Goal | HH Goal Adjustments | Adjusted HHs Served Goal | % of Goal Met | September target % of Goal is 40%
ABC |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | [12 empty] | 3 | 0.17647 | 6 |  | 6 | 50% | NOTE: Household served goal for the ESG is 250. Partner goals total 234, but total % of Goal is measured against the 250 program housed goal.
Caritas |  | 0 | 0 | 0 | 4 | 1 | 2 | 1 | 2 | [12 empty] | 10 | 1.5882 | 37 |  | 37 | 27.03%
FFH |  | 0 | 0 | 0 | 6 | 2 | 1 | 4 | 0 | [12 empty] | 13 | 0.29412 | 18 |  | 18 | 72.22%
FS |  | 0 | 0 | 0 | 0 | 4 | 2 | 1 | 0 | [12 empty] | 7 | 1.7647 | 37 |  | 37 | 18.92%
LW |  | 0 | 0 | 0 | 3 | 3 | 1 | 17 | 1 | [12 empty] | 25 | 0.88235 | 40 |  | 40 | 62.5%
SA |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [13 empty] | 5 | 2.4118 | 46 |  | 46 | 10.87%
TSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | [12 empty] | 9 | 1.6471 | 37 |  | 37 | 24.32%
Vivent |  | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | [12 empty] | 6 | 0.41176 | 13 |  | 13 | 46.15%
TOTALS |  | 0 | 0 | 0 | 13 | 10 | 8 | 42 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 10.1176 | 234 |  | 250 | 31.2%
Households Housed
Agency |  | HHs Housed (Feb 2021) | HHs Housed (March 2021) | HHs Housed (April 2021) | HHS Housed (May 2021) | HHs Housed (June 2021) | HHs Housed (July 2021) | HHs Housed (Aug 2021) | HHs Housed (Sept 2021) | HHs Housed (Oct 2021) | HHs Housed (Nov 2021) | HHs Housed (Dec 2021) | HHs Housed (Jan 2022) | HHs Housed (Feb 2022) | HHs Housed (March 2022) | HHs Housed (April 2022) | HHs Housed (May 2022) | HHs Housed (June 2022) | HHs Housed (July 2022) | HHs Housed (Aug 2022) | HHs Housed (Sept 2022) | HHs Housed YTD | Average per month to attain goal | Household Housed Goal | HH Housed Goal Adjustments | Adjusted HHs Housed Goal | % of Goal Met | August target % of Goal is 35%
ABC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0.29412 | 5 |  | 5 | 0% | NOTE: Household housed goal for the ESG is 200. Partner goals total 190, but total % of Goal is measured against the 200 program housed goal.
Caritas |  | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | [12 empty] | 4 | 1.5294 | 30 |  | 30 | 13.33%
FFH |  | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | [12 empty] | 7 | 0.47059 | 15 |  | 15 | 46.67%
FS |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | [12 empty] | 4 | 1.5294 | 30 |  | 30 | 13.33%
LW |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [12 empty] | 2 | 1.7647 | 32 |  | 32 | 6.25%
SA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 2.1765 | 37 |  | 37 | 0%
TSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 1.7647 | 30 |  | 30 | 0%
Vivent |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0.64706 | 11 |  | 11 | 0%
TOTALS |  | 0 | 0 | 0 | 0 | 2 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 10.7647 | 190 |  | 200 | 8.5%
DAYS TO HOUSING
Days to housing - Starting from 2/1/21 - YTD | [21 empty] | Total housed | Average # of days* | Exited without move-in
ABC RRH | [21 empty] | 0 | 0 | 0 | Color key: Green denotes decrease in days. Red denotes increase in days. Black denotes no change.
Caritas RRH | [21 empty] | 4 | 45 | 0
FFH RRH | [21 empty] | 21 | 53 | 2
FS RRH | [21 empty] | 4 | 69 | 0
LW RRH | [21 empty] | 3 | 54 | 0
SA RRH | [21 empty] | 0 | 0 | 0
TSA RRH | [21 empty] | 0 | 0 | 0
Vivent RRH | [21 empty] | 0 | 0 | 0
Collaborative | [21 empty] | 32 | 54 | 2
*Collaborative average # of days to move-in from entry is total averages days/# of partners with RRH enrollments
Quarterly Data
Agency |  | Quarter 1 |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Quarter 5 |  |  | Quarter 6 |  |  | Quarter 7 |  |  | Goal = 80%
|  | HH served | HH housed | HH served | HH housed | Q2 % | HH served | HH housed | Q3 % | HH served | HH housed | Q4 % | HH served | HH housed | Q5 % | HH served | HH housed | Q6 % | HH served | HH housed | Q7 % | YTD total
ABC |  | 0 | 0 | 0 | 0 | #DIV/0! | [15 empty] | #DIV/0!
Caritas |  | 0 | 0 | 5 | 1 | 20% | [15 empty] | 20%
FFH |  | 0 | 0 | 8 | 0 | 0% | [15 empty] | 0%
FS |  | 0 | 0 | 4 | 0 | 0% | [15 empty] | 0%
LW |  | 0 | 0 | 6 | 1 | 16.67% | [15 empty] | 16.67%
SA |  | 0 | 0 | 0 | 0 | #DIV/0! | [15 empty] | #DIV/0!
TSA |  | 0 | 0 | 0 | 0 | #DIV/0! | [15 empty] | #DIV/0!
Vivent |  | 0 | 0 | 0 | 0 | #DIV/0! | [15 empty] | #DIV/0!
TOTALS |  | 0 | 0 | 23 | 2 | 8.696% | [15 empty] | 8.696%
Clients Served
Agency |  | Quarter 1 |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Quarter 5 |  |  | Quarter 6 |  |  | Quarter 7 |  |  | YTD total
ABC |  | 0 |  | 0 | [17 empty] | 0
Caritas |  | 0 |  | 5 | [17 empty] | 5
FFH |  | 0 |  | 22 | [17 empty] | 22
FS |  | 0 |  | 4 | [17 empty] | 4
LW |  | 0 |  | 8 | [17 empty] | 8
SA |  | 0 |  | 0 | [17 empty] | 0
TSA |  | 0 |  | 0 | [17 empty] | 0
Vivent |  | 0 |  | 0 | [17 empty] | 0
TOTALS |  | 0 |  | 39 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 39